## Sheet1
Sprint1 | 04/08/2020 - 15/08/2020
Backlog1: | As a business owner, I want to register my business
Backlog2: | As a user I want to be able to create an account so that I can use the system to manage/book appointments
Backlog3: | As a customer I want to be able to log into the system to manage my bookings
Day | Backlog1 | backlog2 | Backlog3
0 | N/A | N/A | N/A
1 | 0% | 10% | 0%
2 | 0% | 20% | 0%
3 | 10% | 50% | 0%
4 | 10% | 70% | 0%
5 | 20% | 100% | 0%
6 | 40% | 100% | 20%
7 | 50% | 100% | 40%
8 | 70% | 100% | 50%
9 | 85% | 100% | 70%
10 | 100% | 100% | 90%
11 | 100% | 100% | 100%
Sprint2 | 16/08/2020 - 28/08/2020
Backlog1: | As an admin I want to be able to log into the system to view my dashboard
Backlog2: | As a worker I want to be able to log into the system to provide and check my availability
Backlog3: | As a customer I want to be able to view the available days and times so I can find a day for my booking that is convenient for me
Backlog4: | As a customer I want to have a page where I can look up the time using a search function, and select an appointment type so that I can find a booking more easily
Day | Backlog1 | backlog2 | Backlog3 | Backlog4
0 | N/A | N/A | N/A | N/A
1 | 40% | 0% | 10% | 0%
2 | 85% | 0% | 20% | 0%
3 | 100% | 0% | 40% | 10%
4 | 100% | 50% | 50% | 20%
5 | 100% | 100% | 60% | 45%
6 | 100% | 100% | 70% | 60%
7 | 100% | 100% | 90% | 70%
8 | 100% | 100% | 100% | 80%
9 | 100% | 100% | 100% | 90%
10 | 100% | 100% | 100% | 100%
11 | 100% | 100% | 100% | 100%
12 | 100% | 100% | 100% | 100%
Sprint3 | 01/09/2020 - 11/09/2020
Backlog1: | As a customer I want to be able to view my previous bookings to see when my previous appointments were
Backlog2: | As a customer I want to be able to edit my details so that if my address or phone number changes I can still be contacted
Backlog3: | As a customer I want to be able to book an appointment for a given date, time, and worker so that I can keep my day to day life organized
Backlog4: | As a customer I want to be able to cancel a booking so that if I am unable to attend, I will not be charged for the appointment
Day | Backlog1 | backlog2 | Backlog3 | Backlog4
0 | N/A | N/A | N/A | N/A
1 | 10% | 20% | 10% | 10%
2 | 25% | 45% | 20% | 30%
3 | 50% | 60% | 40% | 50%
4 | 50% | 80% | 50% | 70%
5 | 80% | 100% | 60% | 100%
6 | 100% | 100% | 75% | 100%
7 | 100% | 100% | 80% | 100%
8 | 100% | 100% | 95% | 100%
9 | 100% | 100% | 100% | 100%
10 | 100% | 100% | 100% | 100%
11 | 100% | 100% | 100% | 100%
Sprint4 | 22/09/2020 - 06/10/2020
Backlog1: | As a worker I want to be able to provide my availability so that I am able to preserve my work-life balance
Backlog2: | As an admin I want to be able to manage bookings so that if something happens on the business side I am able to indicate that a booking is no longer available
Backlog3: | As an admin I want to be able to manage the available times and workers for the next month so that my customers don't make bookings that my business cannot keep
Day | Backlog1 | backlog2 | Backlog3
0 | N/A | N/A | N/A
1 | 20% | 0% | 0%
2 | 50% | 0% | 10%
3 | 70% | 25% | 25%
4 | 100% | 60% | 40%
5 | 100% | 80% | 55%
6 | 100% | 100% | 65%
7 | 100% | 100% | 75%
8 | 100% | 100% | 80%
9 | 100% | 100% | 90%
10 | 100% | 100% | 100%
11 | 100% | 100% | 100%
12 | 100% | 100% | 100%
13 | 100% | 100% | 100%
14 | 100% | 100% | 100%
15 | 100% | 100% | 100%